## BIM Deliverables - Guidelines
BIM Submittal Item | BIM Submittal Item | File Sender/ Author | File Received/ Location | Submitted or Available | Stage | Frequency of Occurrence | Deliverable Due/Start Date | Finish Date | File type | Notes | BIM Submittal Item | BIM Submittal Item | Submitted or Available | Stage | Frequency of Occurrence | Notes
|  | Use company names here, if available. | Indicate the model exchange tool, document management system, or CDE name. Provide a hyperlink if possible. | Available |  | Once, weekly, monthly, or other frequency of occurance. | Start date for recurring deliverables or due date for one-time deliverables. | Finish data for recurring deliverables. Leave blank for one-time deliverables. | Ex. RVT, DWG, XLS, DOC
BIM Execution Planning | BIM Execution Plan (Design) |  |  | Submitted | Schematic Design | Once |  |  |  | BEP should be reviewed with UCSD PM Team and Data Manager. | BIM Execution Planning | BIM Execution Plan (Design) | Submitted | Schematic Design | Once | BEP should be reviewed with UCSD PM Team and Data Manager.
| BIM Execution Plan (Construction) |  |  | Submitted | Preconstruction | Once |  |  |  | Review BEP plan with UCSD PM and Data Manager, updated by the CM/GC and trade partners model authors. |  | BIM Execution Plan (Construction) | Submitted | Preconstruction | Once | Review BEP plan with UCSD PM and Data Manager, updated by the CM/GC and trade partners model authors.
Design Authoring | Schematic Design Phase Models for Review |  |  | Available | Schematic Design | Biweekly |  |  |  | Current RVT or native model files to be uploaded to model collaboration platform or University system-of-record at major SD milestone reviews. | Design Authoring | Schematic Design Phase Models for Review | Available | Schematic Design | Biweekly | Current RVT or native model files to be uploaded to model collaboration platform or University system-of-record at major SD milestone reviews.
| Design Development Models for Review |  |  | Available | Design Development | Biweekly |  |  |  | Current RVT or native model files to be uploaded to model collaboration platform or University system-of-record at major DD milestone reviews. |  | Design Development Models for Review | Available | Design Development | Biweekly | Current RVT or native model files to be uploaded to model collaboration platform or University system-of-record at major DD milestone reviews.
| Construction Document Models for Review |  |  | Available | Construction Documents | Biweekly |  |  |  | Current RVT or native model files to be uploaded to model collaboration platform or University system-of-record at major CD milestone reviews. |  | Construction Document Models for Review | Available | Construction Documents | Biweekly | Current RVT or native model files to be uploaded to model collaboration platform or University system-of-record at major CD milestone reviews.
3D Coordination | Design Coordination Reports (DD) |  |  | Submitted | Design Development | Monthly |  |  |  | Reports should indicate major areas of design coordination issues, issue status, action required by when, team member(s) issue assignment. | 3D Coordination | Design Coordination Reports (DD) | Submitted | Design Development | Monthly | Reports should indicate major areas of design coordination issues, issue status, action required by when, team member(s) issue assignment.
| Design Coordination Reports (CD) |  |  | Submitted | Construction Documents | Monthly |  |  |  | Reports should have more detailed coordination items organized by discipline compared to the high-level DD coordination reports. |  | Design Coordination Reports (CD) | Submitted | Construction Documents | Monthly | Reports should have more detailed coordination items organized by discipline compared to the high-level DD coordination reports.
| Construction Models (for Coordination) |  |  | Available | Construction | Weekly |  |  |  | Native models developed for coordination and shop drawings and any exports required for the coordination process. |  | Construction Models (for Coordination) | Available | Construction | Weekly | Native models developed for coordination and shop drawings and any exports required for the coordination process.
Space Management | Schematic Design Drawing Sets |  |  | Submitted | Schematic Design | Once |  |  |  | PDF drawing sets. See UCSD CAD Standard (Attachment 6). | Space Management | Construction Documents Drawing Sets | Submitted | Construction Documents | Once | PDF drawing sets. See UCSD CAD Standard (Attachment 6).
| Construction Documents Drawing Sets |  |  | Submitted | Construction Documents | Once |  |  |  | PDF drawing sets. See UCSD CAD Standard (Attachment 6). |  | Construction Documents Drawing Sets | Submitted | Construction Documents | Once | PDF drawing sets. See UCSD CAD Standard (Attachment 6).
| Space Management Floorplans (CD) |  |  | Submitted | Construction Documents | Once |  |  |  | CAD exports from space management views stored in architectural models. See BIM Guidelines Attachment 3, 5, and 6. |  | Space Management Floorplans (CD) | Submitted | Construction Documents | Once | CAD exports from space management views stored in architectural models. See BIM Guidelines Attachment 3, 5, and 6.
| Space Management Floorplans (Closeout) |  |  | Submitted | Closeout | Once |  |  |  | CAD exports from space management views stored in architectural models. See BIM Guidelines Attachment 3, 5, and 6. |  | Space Management Floorplans (Closeout) | Submitted | Closeout | Once | CAD exports from space management views stored in architectural models. See BIM Guidelines Attachment 3, 5, and 6.
Model Data Quality | Design Models with MMD for Review |  |  | Submitted | Construction | Once |  |  |  | Design models from design authoring, if identified as storing min model data (MMD) based on LOD Matrix, will be reviewed by Data Author for completeness of MMD at some point after 100% CD's or equivalent. | Model Data Quality | Design Models with MMD for Review | Submitted | Construction | Once | Design models from design authoring, if identified as storing min model data (MMD) based on LOD Matrix, will be reviewed by Data Author for completeness of MMD at some point after 100% CD's or equivalent.
| Trade Models with MMD for Review |  |  | Submitted | Construction | Once |  |  |  | Trade models from trade coordination, if identified as storing min model data (MMD) based on LOD Matrix, will be reviewed by Data Author for completeness of MMD at some point after trade coordination. |  | Trade Models with MMD for Review | Submitted | Construction | Once | Trade models from trade coordination, if identified as storing min model data (MMD) based on LOD Matrix, will be reviewed by Data Author for completeness of MMD at some point after trade coordination.
Record Modeling | Record Documents Drawing Sets |  |  | Submitted | Closeout | Once |  |  |  | PDF drawing sets. See UCSD CAD Standard (Attachment 6). | Record Modeling | Record Documents Drawing Sets | Submitted | Closeout | Once | PDF drawing sets. See UCSD CAD Standard (Attachment 6).
| Record Models |  |  | Submitted | Closeout | Once |  |  |  | The record model will become the University as-managed model. All assets identified in the FDS should be represented within UCSD-specified tolerances for record models. Facility data deliverables should align back to record models. Revit highly preferred. |  | Record Models | Submitted | Closeout | Once | The record model will become the University as-managed model. All assets identified in the FDS should be represented within UCSD-specified tolerances for record models. Facility data deliverables should align back to record models. Revit highly preferred.
As-Built Modeling | As-Built Models |  |  | Submitted | Closeout | Once |  |  |  | As-built models will be used for reference in facility operations to represent the most accurate location of distribution and routings. | As-Built Modeling | As-Built Models | Submitted | Closeout | Once | As-built models will be used for reference in facility operations to represent the most accurate location of distribution and routings.
*Other BIM Use* | BIM Submission Item 1 | [8 empty] | *Use this row to add other BIM submissions for BIM Uses that are specific to the project.
| BIM Submission Item 2 | [8 empty] | *Use this row to add other BIM submissions for BIM Uses that are specific to the project.
| BIM Submission Item 3 | [8 empty] | *Use this row to add other BIM submissions for BIM Uses that are specific to the project.
Note on G2: Enter the project-specific list of project stages in the "Project Stages" worksheet. Make sure these align with stages used in Section 1 of the BEP.
Note on S2: Enter the project-specific list of project stages in the "Project Stages" worksheet. Make sure these align with stages used in Section 1 of the BEP.

## Facility Data Deliverables
|  |  |  | 100% SD |  | 100% DD |  | 100% CD |  | Product Data Submittals Phase 1 |  | Product Data Submittals Phase "N" |  | Startup Reports |  | Commissioning |  | Substantial Completion
|  |  |  | 2030-01-01 |  | 2030-01-01 |  | 2030-01-01 |  | 2030-01-01 |  | 2030-01-01 |  | 2030-01-01 |  | 2030-01-01 |  | 2030-01-01
*Delete This Column After Completion* | Deliverable Description | Responsible Party | Tool | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual
| Facility Data Plan | Project Team Lead | [5 empty] | 2022-01-05
| Project-Specific FDS | Project Team Lead
| Facility Data Deliverables Schedule | Project Team Lead
| Locations Table | Architect
| Data Drop 1 Inventory - Architect | Architect | [17 empty] | Assets | $ of Total
| Data Drop 1 Inventory - Mechanical Trade Partner | Mechanical Trade Partner
| Data Drop 1 Inventory - Plumbing Trade Partner | Plumbing Trade Partner
| Data Drop 1 Inventory - Electrical Trade Partner | Electrical Trade Partner
| Data Drop 1 Inventory - Curtain Wall and Glazing Trade | Curtain Wall and Glazing Trade
| Data Drop 1 Inventory - Plumbing Trade Partner | Plumbing Trade Partner
| Data Drop 2 Product - Electrical Trade Partner | Electrical Trade Partner | [17 empty] | 1000 | 46.51%
Delete row if not needed | Data Drop 2 Product - Curtain Wall and Glazing Trade | Curtain Wall and Glazing Trade | [17 empty] | 500 | 23.26%
Delete row if not needed | Data Drop 2 Product - *Enter Data Author Here* | *Enter Data Author Here* | [17 empty] | 200 | 9.302%
Delete row if not needed | Data Drop 2 Product - *Enter Data Author Here* | *Enter Data Author Here* | [17 empty] | 50 | 2.326%
Delete row if not needed | Data Drop 2 Product - *Enter Data Author Here* | *Enter Data Author Here* | [17 empty] | 300 | 13.95%
Delete row if not needed | Data Drop 2 Product - *Enter Data Author Here* | *Enter Data Author Here* | [17 empty] | 100 | 4.651%
| Data Drop 3 Serial - *Enter Data Author Here* | *Enter Data Author Here*
Delete row if not needed | Data Drop 3 Serial - *Enter Data Author Here* | *Enter Data Author Here*
Delete row if not needed | Data Drop 3 Serial - *Enter Data Author Here* | *Enter Data Author Here*
Delete row if not needed | Data Drop 3 Serial - *Enter Data Author Here* | *Enter Data Author Here*
Delete row if not needed | Data Drop 4 Barcode - *Enter Data Author Here* | *Enter Data Author Here*
Delete row if not needed | HDH Maximo Asset Table | *Enter Data Author Here*
Delete row if not needed | HDH Maximo Location Table | *Enter Data Author Here*
Delete row if not needed | FM Maximo Asset Table | *Enter Data Author Here*
Delete row if not needed | FM Maximo Location Table | *Enter Data Author Here*
Delete row if not needed | MC CMMS Asset Table | *Enter Data Author Here*
Delete row if not needed | Total Complete | *Enter Data Author Here*
Delete row if not needed | Remaining Planning | *Enter Data Author Here*
Delete row if not needed | Facility Data Plan | *Enter Data Author Here*
Delete row if not needed | Project-Specific FDS | *Enter Data Author Here*
Delete row if not needed | Facility Data Deliverables Schedule | *Enter Data Author Here*
Delete row if not needed | Data Drop 1 - All Disciplines | *Enter Data Author Here*
Delete row if not needed | Data Drop 2 - Mechanical | *Enter Data Author Here*
Delete row if not needed | Data Drop 2 - Electrical | *Enter Data Author Here*
Delete row if not needed | Data Drop 2 - Plumbing | *Enter Data Author Here*
Delete row if not needed | Data Drop 2 - Civil | *Enter Data Author Here*
Delete row if not needed | Data Drop 2 - Architectural | *Enter Data Author Here*
Delete row if not needed | Data Drop 2 - Miscellaneous | *Enter Data Author Here*
Delete row if not needed | Data Drop 3 - Mechanical | *Enter Data Author Here*
Delete row if not needed | Data Drop 3 - Electrical | *Enter Data Author Here*
Delete row if not needed | Data Drop 3 - Plumbing | *Enter Data Author Here*
Delete row if not needed | Data Drop 3 - Miscellaneous | *Enter Data Author Here*
Delete row if not needed | Data Drop 4 - Barcodes | *Enter Data Author Here*
Delete row if not needed | HDH Maximo Asset Table | *Enter Data Author Here*
Delete row if not needed | HDH Maximo Location Table | *Enter Data Author Here*
Delete row if not needed | FM Maximo Asset Table | *Enter Data Author Here*
Delete row if not needed | FM Maximo Location Table | *Enter Data Author Here*
Delete row if not needed | MC CMMS Location Table | *Enter Data Author Here*
Note on A7: Sean Doolan: A facilities column may be added for projects with multiple facilities.

## Lookup
Project Phases | Data Authors *List Company Names Below* | Tools
Programming | Architect | eBuilder
Schematic Design | Construction Manager | BIM 360 Docs
Design Development | Mechanical Trade Partner | Procore
Construction Documents | Plumbing Trade Partner | Bluebeam Studio
Procurement/Bid (CM/GC) | Electrical Trade Partner | VueOps
Preconstruction | Curtain Wall and Glazing Trade
Buyout (Subs) | DFH Sub
Construction | Data Manager
Pre-Closeout
Commissioning
Closeout
Post-Occupancy
Facility Operations